## CapEx Tracker
CapEx Project Tracker — Multifamily Portfolio
Last Updated: March 25, 2026 ¦ Total Budget: $720,000 ¦ Spent: $243,500 ¦ Remaining: $476,500 ¦ % Spent: 33.8%
Project Name | Property | Scope | Total Budget | Spent to Date | Budget Remaining | Vendor / Contractor | Start Date | Est. Completion | Owner's Rep | Status | % Complete | Priority | Next Action | Notes
Park Layne Structural | Park Layne | Structural | 350000 | 230000 | 120000 | Hart Restoration | — | Apr 15, 2026 | Nate Fisher | AT RISK | 65% | HIGH | Get written milestone schedule from Hart confirming $120K scope closes by Apr 15 | 21 days to deadline with $120K remaining — aggressive
Park Layne Insurance | Park Layne | Insurance Work | 100000 | 0 | 100000 | Sturgeon Contracting | — | Apr 15, 2026 | Stephen B | AT RISK | 0% | HIGH | Call Sturgeon today — confirm start date in writing | $0 spent against Apr 15 deadline is a critical gap
Park Layne Roof | Park Layne | Roofing | 100000 | 5500 | 94500 | NONE | — | May 1, 2026 | Stephen B | AT RISK | 5% | HIGH | Solicit 3 roofing bids immediately; award by Apr 1 | No contractor — $94.5K of work with 37 days to go
Executive House 808 Fire Unit | Executive House | Fire / Interior Restoration | 60000 | 3000 | 57000 | NONE | — | May 1, 2026 | UNASSIGNED | AT RISK | 5% | HIGH | Assign Owner's Rep today; hire GC this week; initiate MEP coordination | No OR, no GC — fire/life safety scope cannot sit unmanaged
Executive House 803 | Executive House | Renovation | 15000 | 4000 | 11000 | NONE | — | NONE | Stephen B | AT RISK | 25% | MEDIUM | Hire GC and set hard completion date — plans submitted, no excuse for further delay | No contractor, no timeline
Riverstone 309 | Riverstone | Interior — Kitchen & Bath | 15000 | 0 | 15000 | NONE | — | Apr 15, 2026 | Stephen B | AT RISK | 0% | HIGH | Award interior contractor this week — consider same contractor as 403 for concurrent runs | $0 spent, no contractor, 21 days out
Riverstone 403 | Riverstone | Interior — Kitchen & Bath | 15000 | 0 | 15000 | NONE | — | Apr 15, 2026 | Stephen B | AT RISK | 0% | HIGH | Hire interior contractor immediately — same urgency as 309; confirm one contractor can run both units concurrently | Separate unit confirmed; same scope as 309
Riverstone Steps | Riverstone | Exterior — Concrete Steps | 15000 | 1000 | 14000 | NONE | — | May 1, 2026 | Stephen B | AT RISK | 7% | MEDIUM | Hire concrete contractor; $1K likely mobilization/demo only | No contractor assigned
Executive House Fire Panel | Executive House | Fire Panel System | 50000 | 0 | 50000 | Koorsen Fire | — | May 1, 2026 | Nate Fisher | NOT STARTED | 0% | HIGH | Confirm Koorsen mobilization date and permit status — fire panel is life safety, no slippage acceptable | Vendor assigned; must confirm start

## Risk & Actions
Risk Summary & Next Actions — As of March 25, 2026
🚨 AT-RISK PROJECTS
Project | Owner / Spent | Status / Days | Action / Note
Park Layne Insurance | Stephen B | CRITICAL | Call Sturgeon Contracting today — confirm start date in writing. $0 spent, Apr 15 deadline, 21 days out.
Executive House 808 Fire Unit | UNASSIGNED | CRITICAL | Assign Owner's Rep today. Hire GC this week. Initiate MEP coordination. Fire/life safety — cannot sit unmanaged.
Riverstone 309 | Stephen B | CRITICAL | Award interior contractor this week. Consider same contractor as 403 to run both units concurrently.
Riverstone 403 | Stephen B | CRITICAL | Hire interior contractor immediately. Same urgency as 309. Apr 15 is 21 days out with $0 spent.
Park Layne Structural | Nate Fisher | HIGH | Get written milestone schedule from Hart confirming $120K of work closes by Apr 15.
Park Layne Roof | Stephen B | HIGH | Solicit 3 roofing bids immediately. Award contract by Apr 1 or May 1 deadline is lost.
Executive House 803 | Stephen B | HIGH | Hire GC and set hard completion date. Plans are submitted — no reason for further delay.
Riverstone Steps | Stephen B | MEDIUM | Hire concrete contractor. $1K of spend is likely mobilization/demo only.
💰 BUDGET WATCH
Project | Owner / Spent | Status / Days | Action / Note
Park Layne Structural | $230K / $350K | 65.7% spent | $120K remaining with 21 days to go — confirm scope is achievable.
Park Layne Insurance | $0 / $100K | 0% spent | Full budget uncommitted, deadline in 21 days.
Park Layne Roof | $5.5K / $100K | 5.5% spent | $94.5K uncommitted, no contractor.
Executive House 808 | $3K / $60K | 5% spent | Fire scope, no GC — $57K at risk.
Executive House Fire Panel | $0 / $50K | 0% spent | Vendor assigned; must confirm mobilization.
PORTFOLIO TOTAL | $243.5K / $720K | 33.8% spent | $476.5K uncommitted across 9 projects.
⏱ TIMELINE ISSUES
Project | Owner / Spent | Status / Days | Action / Note
Park Layne Insurance | Apr 15 | 21 days | 0% spent — CRITICAL
Riverstone 309 | Apr 15 | 21 days | 0% spent, no contractor — CRITICAL
Riverstone 403 | Apr 15 | 21 days | 0% spent, no contractor — CRITICAL
Park Layne Structural | Apr 15 | 21 days | $120K remaining — HIGH
Park Layne Roof | May 1 | 37 days | No contractor — HIGH
Executive House 808 | May 1 | 37 days | No GC, no OR — HIGH
Executive House Fire Panel | May 1 | 37 days | Vendor assigned, not started — MEDIUM
Riverstone Steps | May 1 | 37 days | No contractor — MEDIUM
Executive House 803 | NONE | — | No completion date set — HIGH

## Next Actions
Next Actions — Grouped by Owner's Rep
Nate Fisher
Project | Priority | Action
Park Layne Structural | HIGH | Get written milestone schedule from Hart confirming $120K scope closes by Apr 15. Immediately.
Executive House Fire Panel | HIGH | Confirm Koorsen mobilization date and permit status. Fire panel is life safety — no slippage acceptable.
Stephen B
Project | Priority | Action
Park Layne Insurance | HIGH | Call Sturgeon Contracting TODAY — confirm start date in writing. Apr 15 is 21 days out with $0 spent.
Park Layne Roof | HIGH | Solicit 3 roofing bids immediately. Award contract by Apr 1 hard deadline.
Executive House 803 | MEDIUM | Hire GC and set hard completion date this week. Plans are submitted.
Riverstone 309 | HIGH | Award interior contractor this week. Consider same contractor as 403 for concurrent execution.
Riverstone 403 | HIGH | Hire interior contractor immediately. Same urgency as 309.
Riverstone Steps | MEDIUM | Hire concrete contractor. Provide mobilization date.
UNASSIGNED — Escalate Now
Project | Priority | Action
Executive House 808 Fire Unit | HIGH | Assign Owner's Rep TODAY. Then: hire GC, initiate MEP coordination. Fire/life safety — cannot be managed by committee.